## Slide 1: CSE 403
Classic Mistakes
Reading:
Rapid Development Ch3
These lecture slides are copyright (C) Marty Stepp, 2007, with significant content taken from slides written by Valentin Razmov. They may not be rehosted, sold, or modified without expressed permission from the author. All rights reserved.

## Slide 2: What is a software project?
Projects are a balance of three dimensions, with the goal of producing a successful deliverable.
FEATURES
TIME
RESOURCES
SOFTWARE
DELIVERABLE

## Slide 3: The goal of building software
A successful deliverable is characterized by being:
  on time
  on budget
  with good quality
"Good, Fast and Cheap. Choose two!"
Which two would you pick for a project like yours?
  Good and Fast, but not Cheap
  Good and Cheap, but not Fast
  Fast and Cheap, but not Good

## Slide 4: The fate of software projects
Under some reasonable definition of a "project" (you decide on it), what would you guess is the percentage of software projects that fail to accomplish their goals?
Choose the range in which your estimate falls:
  0-20%
  20-40%
  40-60%
  60-80%
  80-100%

## Slide 5: Answers
Here is how undergraduate students in software engineering (CSE 403) voted (left) vs. how graduate students (in CSE 590ET) voted (right):
Historically, nearly 85% of software projects fail.

## Slide 6: Why do projects fail?
What were some of the reasons given for the failure of the software project in the anecdote in Rapid Development section 3.1?

## Slide 7: Why do projects fail? 2
Some reasons the "Giga Quote" project failed:
  management set unrealistic expectations; Mike didn't correct them
  overestimated the positive impact of tools (C++, OO, new hardware)
  hired developers based on availability despite warning signs
  personality conflicts between developers
  changes in rate structure requirements in middle of work
  one delay causes another (dev delay leads to test delay, etc.)
  hacks and shortcuts (bar chart and report on same page)
  developers end up working "death marches" (6-day, 10-hour weeks)
  overestimating how nearly done you are ("I'm 90% done")
  software didn't match the spec (company logo not on every page)
  developer time taken away by other tasks (Jill moonlighting, etc.)
  once software was delivered to be tested, tons of bugs came out
  developers didn't listen to testers; ignored severity of bugs reported
  management promised big bonuses, gave tiny ones

## Slide 8: People
Undermined motivation
Weak personnel
Uncontrolled problem employees
Heroics
Adding people to a late software project
Noisy, crowded offices
Friction between developers and customers
Unrealistic expectations
Lack of effective project sponsorship
Lack of stakeholder buy-in
Lack of user input
Politics placed over substance
Wishful thinking

## Slide 9: Process
Overly optimistic schedules
Insufficient risk management
Contractor failure
Insufficient planning
Abandonment of planning under pressure
Wasted time during the "fuzzy front end"
Shortchanged upstream activities
Inadequate design
Shortchanged quality assurance
Insufficient management controls
Premature or overly frequent convergence
Omitting necessary tasks from estimates
Planning to catch up later
Code-like-hell programming

## Slide 10: Product
Requirements gold-plating
Feature creep
Developer gold-plating
Push-me, pull-me negotiation
Research-oriented development

## Slide 11: Technology
Silver-bullet syndrome
Overestimated savings from new tools or methods
Switching tools in the middle of a project
Lack of automated source-code control

## Slide 12: Mistake comparison table
People | Process | Product | Technology
Undermined motivation Weak personnel Uncontrolled problem employees Heroics Adding people to a late software project Noisy, crowded offices Friction between developers and customers Unrealistic expectations Lack of effective project sponsorship Lack of stakeholder buy-in Lack of user input Politics placed over substance Wishful thinking | Overly optimistic schedules Insufficient risk management Contractor failure Insufficient planning Abandonment of planning under pressure Wasted time during the "fuzzy front end" Shortchanged upstream activities Inadequate design Shortchanged quality assurance Insufficient management controls Premature or overly frequent convergence Omitting necessary tasks from estimates Planning to catch up later Code-like-hell programming | Requirements gold-plating Feature creep Developer gold-plating Push-me, pull-me negotiation Research-oriented development | Silver-bullet syndrome Overestimated savings from new tools or methods Switching tools in the middle of a project Lack of automated source-code control

## Slide 13: Is software different?
Is software engineering different from other engineering disciplines in this regard?

## Slide 14: Arguments in favor
Is software engineering different from other engineering disciplines in this regard?
  Arguments in favor:
  testing the quality of software is harder
    the Halting Problem presents a fundamental limitation in the extent to which software quality can be evaluated
      Most properties of software that we care about are unverifiable
    unlike bridges and buildings where everything can be tested using known procedures
  much higher rate of failure
  lower barrier to entry
  immaturity of the discipline
  customer expectations: quality, delivery timeline, etc.
  frantic rate of technological change
  software is easier to copy

## Slide 15: Arguments against
Is software engineering different from other engineering disciplines in this regard?
  Arguments against:
  software isn't "soft"
    contrary to popular perception, change cannot be easily accommodated, yet requirements do change
    in reality, even though change is possible in principle, accommodating change often forces a rewriting of major parts of the software
  software developers still need to plan, execute, test, and sell their products
  the discipline is still in its infancy