## Slide 1: CSE 403
Scheduling
These lecture slides are copyright (C) Marty Stepp, 2007, with significant content taken from slides written by Valentin Razmov. They may not be rehosted, sold, or modified without expressed permission from the author. All rights reserved.

## Slide 2: A late software project
In the graph below, the project was supposed to reach milestone A in 1 month (left), but in fact it took 2 months (right).
  How should this delay be interpreted?
  What are the options facing the project's manager?
  Should the manager add extra people to the development team to make up for the delay? If so, how many and why?

## Slide 3: One interpretation
Only Part A was misestimated, so therefore the overall project is currently going to be 1 month late. (right)
  If the assumption is valid:
    9 man-months of work remain
    / 2 actual months remain in which to do it
    = 4.5 people will need to work each month
    so add 2 workers to the existing 3.

## Slide 4: Another interpretation
The whole project estimate was low, and the project as a whole will take twice as long as expected. (right)
  If the assumption is valid:
    18 man-months of work remain
    / 2 actual months remain in which to do it
    = 9 people will need to work each month
    so add 6 workers to the existing 3.

## Slide 5: The Mythical Man-Month
If we assume the first interpretation was correct:
  We must account for delays in training the new workers
  We must partition the job into 5 pieces, to be integrated later
  Brooks' Law: "Adding manpower to a late software project makes it later." -- The Mythical Man-Month